## product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | Prioirity | Dependencies | Asignee | Status
S1 | S1 | US-001 | BASICS OF PROBABILITY AND STATISTICS [mean,median,mode,harmonic mean,conditional probability,range,variance etc. | SHOULD HAVE | No Dependency | Sathwika | 3- Completed
S1 | S1 | US-001 | PYTHON BASICS [Pandas,numpy,model creation,feeding the model,training the model,testing the model, slicing,indexing] | MUST HAVE | Syntax | Sathwika | 3- Completed
S2 | S2 | US-001 | MACHINE LEARNING BASICS [Introduction,supervised learning,unsupervised learning,deep learning,structed data,unstructured data] | MUST HAVE | Algorithms | Sathwika | 3- Completed
S2 | S2 | US-001 | DATA SETS | SHOULD HAVE | Data | Sathwika | 3- Completed
S3 | S3 | US-001 | DATA SCIENCE BASICS [Introduction,Data collection,Data Cleaning and Preprocessing,Data Analysis, Data visualization] | SHOULD HAVE | Statistics | Sathwika | 3- Completed
S4 | S4 | US-001 | NLP [Over view of NLP, Tokenization(sentence tokenization),Stemming, Lemmatization, Vizualization of tokens, Puntuations,Regular expression.] | MUST HAVE | Lingustics | Sathwika | 3- Completed
S5 | S5 | US-001 | Generative AI [Basics of AI, Models(LLM), Transformer Architecture, Loading CSV files, Loading JSON files, Loading PDF files, word documents] | MUST HAVE | Python | Sathwika | 3- Completed
S6 | S6 | US-001 | RAG [Introduction, Data preparation->Raw data Sources, Chuncking, Embeddings,Vector database, LLMs, Response][ Libraries-> langchain community,PyPDF,PyPDFDirectoryLoader,docx2txt,RecursiveCharacterTextSplitter,fastembed,faiss-cpu, db.as_retriever, groq, langchain-groq, python-dotenv, API, Chatgroq, LLM] | MUST HAVE | Jupyter Notebook | Sathwika | 3- Completed

## SprintBacklog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to project(Form Filling AI) | 2024-11-04 | 2024-11-06 | sathwika | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | Workflow Creation and Project Goal Document | 2024-11-07 | 2024-11-08 | sathwika | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 2024-11-11 | 2024-11-11 | sathwika | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Use Case Research and Preparation | 2024-11-12 | 2024-11-15 | sathwika | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Python practice Kit Completion | 2024-11-16 | 2024-11-22 | sathwika | Coding | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | SQL practice Kit Completion | 2024-11-23 | 2024-11-29 | sathwika | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-07 | Project Discussion Module 1(Voice Input and Language Processing) | 2024-12-02 | 2024-12-06 | sathwika | Build | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Project Discussion Module 2(Workflow Automation and Optimization) | 2024-12-09 | 2024-12-13 | sathwika | Coding | 2- In Progress | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Project Discussion Module 3(Integration with existing services) | 2024-12-16 | 2024-12-20 | sathwika | Integration Test | 2- In Progress | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-10 | Project Discussion Module 4(Testing and Deployment) | 2024-12-23 | 2024-12-27 | sathwika | System Test | 2- In Progress | 8 | Day 1: 3; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 1

## Standup Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity regarding project requirements | Held a detailed discussion with mentor and researched on it.
Sprint 1 | Day 4 | Uncertainty about specific project goals and workflow steps | Conducted a team brainstorming research to review, analyze and finalize the project requirements.
Sprint 2 | Day 6 | Confusion in understanding the Agile template | Organized a meeting with the mentor to clarify all doubts.
Sprint 2 | Day 7 | Difficulty in identifying comprehensive use cases due to incomplete information | Performed additional research and consulted online resources to address gaps.
Sprint 2 | Day 9 | Challenges in prioritizing use cases for implementation | Developed a priority matrix to assess and rank use cases based on importance.
Sprint 3 | Day 12 | Issues with debugging Python practice code | Took help of chatgpt and online resources to troubleshoot and resolve the problem
Sprint 4 | Day 16 | SQL queries taking longer than anticipated | Enhanced query performance with mentor guidance.
Sprint 5 | Day 23 | Difficulties integrating voice processing with workflows | Conducted a team debugging session to address integration challenges.

## Retrospection
S.No | Sprint S.No | Sprint Start Date | Sprint End Date | Team Member Name | Started Doing | Stopped Doing | Continued Doing | Actions taken | Learnings | Improvement areas
1 | Sprint 1 | 2024-12-04 | 2024-12-08 | Sathwika Kurma | Conducted an in-depth exploration of transformer architecture concepts, building a strong foundational understanding. | Eliminated the habit of assuming LLMs as black boxes, transitioning to a mindset focused on understanding core logic. | Engaged actively in team discussions with the mentor, fostering collaborative learning and idea exchange. | Developed a comprehensive mind map of transformers, supplemented by rigorous review through online resources and mentor guidance. | Mastery of transformer fundamentals is a critical enabler for effective utilization of advanced machine learning models. | Enhance practical application during theoretical learning to achieve a balanced and impactful understanding.
2 | Sprint 2 | 2024-12-11 | 2024-12-15 | Sathwika Kurma | Initiated hands-on practice of retrieval techniques for RAG pipelines, reinforcing practical expertise. | Overcame the tendency to delay code implementation due to perfectionism, adopting an iterative and actionable approach. | Strengthened collaboration on preprocessing techniques, contributing to overall team efficiency. | Tested diverse chunking strategies, successfully deploying a robust vector database for efficient information retrieval. | Pragmatic execution of retrieval techniques accelerates project milestones and enriches team outputs. | Maintain focus on execution without overanalyzing details to ensure timely progress.
3 | Sprint 3 | 2024-12-18 | 2024-12-22 | Sathwika Kurma | Dedicated effort to debug FAISS retriever integration issues, enhancing system stability and performance. | Discontinued the practice of disregarding feedback from earlier test cases, shifting to a feedback-driven development cycle. | Maintained modular coding principles to streamline integration and scalability of the system. | Resolved critical bugs in the retriever module, optimizing similarity search and enhancing retrieval accuracy. | Leveraging feedback systematically transforms potential pitfalls into opportunities for improvement. | Foster a culture of early and frequent feedback during testing phases to minimize iterations.
4 | Sprint 4 | 2024-12-25 | 30-12-2024 | Sathwika Kurma | Designed and implemented a user-friendly Gradio interface and advanced to a full-stack framework leveraging Next.js, React, TailwindCSS, MongoDB, and Flask for backend API integration. | Eliminated neglect of UI/UX considerations, adopting a user-centric design philosophy. | Persisted in refining language model responses to enhance the application’s intelligence and interactivity. | Delivered a responsive, dynamic interface and actively integrated user feedback to iterate on the design and functionality. | Prioritizing intuitive interfaces and user feedback drives engagement and satisfaction. | Incorporate real-time user insights throughout the development process to maintain alignment with user expectations.